## Sheet1
Koffi Henry Gigi Matthew Chaeun Wei Slack
Tasks (color coded per person) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Finding Audio File/OS Requriements |  | <--Completed |  |  |  |  | In Progress-->
Finding Image File/OS Requirements |  |  |  |  | 37200 |  | 40000
Documenting UML, Class Diagrams
Documenting UML, Class Diagrams
Desigining all nonplayer objects
Identifying player obligations
Design Reports and Use Cases
Desiging Screen, Background, Button
Setting up Github Repository
Writing Code that loads level items
Designing Object Interfaces
Design Requirements for player
Documenting UML, Class Diagrams
Documenting UML, Class Diagrams
Make Graphic Files For Objects
Create Level Data Files
Document nonplayer object interface
Write player class/variable methods
Writing sound class, finding audio files
Create Mainwindow, button functions
Coding Graphics Class
Testing code refactoring
Object Interaction Implementation
Implementing Makefile
Debug, Stress test, compile audio files
Test and check buttons
Test and load graphic images in objects
Connect to high score server
Implement object handler
Test player motion/actions
Test all nonplayer objects actions
Final Installation/Compilation